## Dashboard v2 Features
Vectrix — Dashboard v2 Feature Tracker
Sprint: 12-13 ¦ Target: Mar 7, 2026 ¦ Owner: Dana Reeves ¦ Last updated: Feb 17, 2026
Linear ID | Feature | Category | Assignee | Sprint | Priority | Status | Notes
VEC-70 | Core dashboard layout redesign | Design/Frontend | Raj + Sofia | 10 | High | Done | Full visual overhaul approved Jan 30
VEC-72 | Endpoint detail view — latency chart | Frontend | Sofia | 10 | High | Done | P50/P95/P99 toggles, 1h/6h/24h range
VEC-73 | Endpoint detail — error rate panel | Frontend | Sofia | 11 | High | Done | Error classification breakdown
VEC-74 | Alert configuration panel | Frontend | Sofia | 11 | High | Done | Slack + PagerDuty + email destinations
VEC-75 | Real-time WebSocket data feed | Frontend | Sofia | 10 | High | Done | 5-second refresh, reconnect on drop
VEC-76 | Request volume chart | Frontend | Sofia | 11 | Medium | Done | Stacked bar, time range aligned with latency chart
VEC-77 | Vectrix Design System v1.0 | Design | Raj | 10 | High | Done | Tokens, components, Figma library published
VEC-78 | Responsive layout (1280px+) | Frontend | Sofia | 11 | Medium | Done | Desktop first; tablet support deferred
VEC-88 | Saved views — create/edit/delete | Frontend | Sofia | 12 | High | In Progress | ~80% done. Tab states finalized with Raj Feb 17.
VEC-89 | Saved views — org sharing | Frontend | Sofia | 13 | High | Not Started | Share view with all org members
VEC-90 | Customizable widget layout | Frontend | Sofia | 13 | Medium | Not Started | Drag/resize on main dashboard canvas
VEC-91 | Per-user layout persistence | Backend | Liam | 13 | Medium | Not Started | Store layout in PostgreSQL per user
VEC-82 | Comparison mode — multi-range queries | Backend + Frontend | Marcus + Sofia | TBD (v2.1) | High | Deferred | Backend query engine changes needed. Dana: 3 customers have asked. Top of v2.1 backlog.
VEC-84 | Dashboard v2 final QA | QA | Sofia + Raj | 13 | High | Not Started | Target complete Mar 3, 2026
VEC-85 | v2 launch communications | Product | Dana | 13 | Medium | Not Started | In-app announcement + email to existing customers

## Summary
Dashboard v2 — Status Summary
Status | Count | % of Total | Notes
Done | 8 | 53% | Core features shipped
In Progress | 1 | 7% | VEC-88 saved views, ~80%
Not Started | 5 | 33% | Sprint 13 items
Deferred | 1 | 7% | VEC-82 comparison mode — v2.1