## Slide 1
Vectrix Labs
Sprint 12 Review
Feb 3 – Feb 14, 2026 | Facilitator: Marcus Webb
Notes: Dana Reeves | February 17, 2026

## Slide 2
Sprint 12 — Metrics
36
Points Committed
28
Points Completed
10
Issues Closed
6
Carried Over
78%
Velocity
Velocity note: Dashboard v2 frontend is the bottleneck. 6 carried-over tickets — all frontend. Sofia flagged late design handoffs from Raj's PTO week as a contributing factor.

## Slide 3
Dashboard v2 — Status
Overall Completion
85%
Core dashboard redesign
✅ Complete
Endpoint detail view (latency chart, P95/P99)
✅ Complete
Alert configuration panel
✅ Complete
Saved views (VEC-88)
⏳ ~80% — in progress
Comparison mode (VEC-82)
🚫 Deferred to v2.1
New launch target: March 7, 2026

## Slide 4
Sprint 12 — Key Decisions
Comparison Mode (VEC-82) — Deferred to v2.1
DECIDED
Owner: Marcus Webb
Backend multi-range aggregation requires 2-3 sprint points. Will not hold v2 launch. Marcus to provide backend spec by Sprint 13 planning. Dana on record: 3 customers have explicitly requested this.
Clerk Auth Migration — COMPLETE
CLOSED
Owner: Liam Nakamura
All 6 customers migrated as of Feb 12. Firebase fallback removed. VEC-52 and VEC-53 closed.
Anya Chen Offer — $158K base, 0.20% equity
APPROVED
Owner: Priya Chandran
Approved by Priya via DM. Final panel Feb 27. Offer to be extended within 48 hours of panel.

## Slide 5
Action Items
Owner
Action
Due
Sofia Gutierrez
Complete saved views panel (VEC-88)
Feb 28
Sofia + Raj
Final v2 QA pass
Mar 3
Liam Nakamura
VEC-47 per-org retention backend
Mar 1
Marcus Webb
Backend scope for VEC-82 (comparison mode)
Sprint 13 planning
Marcus, Dana, Priya
Anya Chen final panel
Feb 27
Priya + Nina
Meridian SOW redlines to Orion Legal
Feb 24
Jordan Okafor
ClickHouse maintenance window alerts
Feb 21